BeSecured

P12 – Personal Cybersecurity Risk Scanner

WEEK 3 DESIGN REPORT

Project Manager: Mohammedreda El Aroui

Version 1.0  |  April 2026  |  Sprint: Week 3 of 10

| Phase | Status |
| --- | --- |
| System Design | In Progress |
| Duration | Owner |
| 10-week project | Devs / PO |

# 1. Project Overview

BeSecured is a 10-week academic project building a lightweight cybersecurity risk scanner for individuals and small organizations with little to no technical background. The tool scans users' environments for common vulnerabilities, computes a risk score (0–100), and presents clear, actionable recommendations through an intuitive dashboard.

This Week 3 report consolidates all System Design sprint outputs:

- System architecture diagram

- Module breakdown: Scanner, Risk Engine, Dashboard, AI module (optional)

- UI wireframes for all 5 core screens

- Full product backlog and risk register

# 2. Sprint Schedule — Week 3 in Context

| Week | Phase | Key Tasks | Owner | Deliverable |
| --- | --- | --- | --- | --- |
| W1 | Kick-off | Finalize charter, repo setup, DoD, tooling | PO / SM | Project Charter |
| W2 | Planning | Backlog, story mapping, risk register, tech stack | PO / SM | Project Plan + Backlog |
| W3 ▶ | System Design | Architecture, modules, data-flow, UI wireframes | Devs / PO | Design Docs & Wireframes |
| W4 | Env. Setup | CI/CD, skeleton codebase, test framework | Devs | Working Dev Env + CI |
| W5 | Scanner | Open ports, passwords, firewall, software checks | Devs | Scanner Module |
| W6 | Risk Engine | Scoring algorithm, severity weights, false-positive layer | Devs | Risk Score Engine |
| W7 | Dashboard | UI, issue list, remediation steps, export | Devs / PO | Dashboard + Export |
| W8 | AI (opt.) | LLM plain-language explanations (if time allows) | Devs | AI Module |
| W9 | Testing | Unit/integration/UAT, bug fixes, privacy audit | All | Test Report |
| W10 | Delivery | Final demo, docs, code freeze, handoff | All | Final Presentation |

# 3. System Architecture

BeSecured follows a clean three-module pipeline. All processing occurs locally — no data is ever stored or transmitted outside the user's device. The architecture below was produced during the Week 3 sprint and represents the agreed system design before development begins.

Figure 1 — BeSecured system architecture: Scanner → Risk Engine → Dashboard (all local)

# 4. Module Breakdown

The four modules below define the full scope of BeSecured. Each has a defined owner, sprint target, purpose, inputs, and outputs. The AI module is optional and will be descoped if Week 8 is at risk.

Figure 2 — Module breakdown: Scanner (W5), Risk Engine (W6), Dashboard (W7), AI optional (W8)

# 5. UI Wireframes

Five screens have been wireframed to guide the Dashboard sprint (W7). Each screen maps to one or more user stories and is designed for non-technical users — plain language, large visual cues, one primary action per screen.

Figure 3 — UI wireframes: Scan Launch · Progress · Risk Score · Issue List · Report Export

| Screen | Name | Key Elements | User Stories |
| --- | --- | --- | --- |
| 1 | Scan Launch | App logo, 'Start Scan' CTA, privacy notice | US-01 · US-08 |
| 2 | Scan Progress | Real-time progress bars per check category | US-02 |
| 3 | Risk Score Dashboard | Large score, colour-coded severity breakdown | US-03 |
| 4 | Issue List + Fix Steps | Colour-coded issue cards with one-line fix hints | US-04 · US-05 |
| 5 | Report Export | Scan metadata, Export PDF and Export HTML buttons | US-06 |

# 6. Product Backlog (User Stories)

Prioritized using MoSCoW. Story points on a Fibonacci scale. Total: 63 pts (Must 37 · Should 8 · Could 5 · Won't/opt. 13).

| ID | User Story | Pts | Priority | Sprint |
| --- | --- | --- | --- | --- |
| US-01 | As a user, I can launch the scanner with one click | 5 | Must | W5 |
| US-02 | As a user, I see a real-time progress bar during the scan | 3 | Should | W5 |
| US-03 | As a user, I receive a risk score (0–100) after each scan | 8 | Must | W6 |
| US-04 | As a user, I can view detected issues sorted by severity | 5 | Must | W7 |
| US-05 | As a user, each issue has a plain-language explanation + fix steps | 8 | Must | W7 |
| US-06 | As a user, I can export my scan report as PDF or HTML | 5 | Should | W7 |
| US-07 | As a user, a false-positive layer cross-checks results before display | 8 | Must | W6 |
| US-08 | As a user, I am informed no personal data is stored/transmitted | 3 | Must | W5 |
| US-09 | As a user, I can re-run a scan and compare results over time | 5 | Could | W8 |
| US-10 | As a user, I can get AI-generated risk explanations (optional) | 13 | Won't (opt.) | W8 |

# 7. Risk Register & Mitigation

Severity scale: 5 = Critical · 4 = High · 3 = Medium. Each risk includes a designated owner and concrete mitigation.

| ID | Risk | Sev. | Level | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Difficulty accessing system data (OS restrictions) | 4 | High | Fallback to limited checks; notify user of reduced accuracy | Devs |
| R-02 | False positives mislead users | 3 | Med | Add validation layer to cross-check results before display | Devs |
| R-03 | Performance degradation during scan | 3 | Med | Apply optimization techniques; cap scan scope if needed | Devs |
| R-04 | Data privacy concerns / legal restrictions | 5 | Critical | No sensitive data stored or transmitted; clear privacy notice in-app | SM / PO |
| R-05 | Team lacks cybersecurity expertise | 3 | Med | Instructor feedback loops; dedicated research time each sprint | All |
| R-06 | Schedule slippage (AI scope creep) | 4 | High | Treat AI as optional; descope if W8 is at risk | PO / SM |

# 8. Success Criteria

| ID | Criterion | Measurable Target |
| --- | --- | --- |
| SC-01 | Application stability | ≥ 95% of test runs execute without critical errors |
| SC-02 | Risk score generation | 100% of valid scans produce a cybersecurity risk score |
| SC-03 | Vulnerability detection | ≥ 80% of known test-case vulnerabilities correctly detected |
| SC-04 | User comprehension | ≥ 80% of test users rate recommendations as clear and useful |
| SC-05 | Usability | A new user completes a full scan in under 5 minutes without help |
| SC-06 | Schedule | All 10 deliverables delivered within the defined weekly schedule |
| SC-07 | Team velocity | ≥ 90% task completion rate per sprint |
| SC-08 | Privacy compliance | Zero sensitive data stored or transmitted outside user's device |

# 9. Next Steps — Week 4

- Set up dev environments for all team members (Python venv + Node/React)

- Configure GitHub: branch protection, PR review rules, GitHub Actions CI/CD pipeline

- Create skeleton codebase: Scanner stub, Risk Engine stub, React project scaffold

- Pre-commit hooks (Husky + eslint / flake8) for code quality enforcement

- Establish unit test framework: pytest (backend) + Jest + React Testing Library (frontend)

- Review architecture and module interfaces with instructor

- Present Week 3 artefacts at Friday sprint review for sponsor feedback

All Week 3 design artefacts are complete and ready for review.

Prepared by: Mohammedreda El Aroui  |  Project Manager, BeSecured P12  |  April 2026