## Info
Project Workbook Information
The project workbook allows project managers, team members, sponsors, and stakeholders to easily track and monitor project activities. Any of these worksheets can easily be broken out into separate documents.
Suggested Sheets for All Projects
Data | Filling out the Data sheet completes the header portion of all remaining sheets in the project workbook.
Minicharter | The Project Minicharter sheet can be used as a charter for small projects or a summarization of a full charter for larger projects.
Stoplight | The Stoplight Report sheet contains a status report that can be used to keep sponsors, team members, and stakeholders informed of project progress.
Budget | The Budget sheet allows you to track original budget, expenditures to date, and any cost variance.
CBA | The Cost/Benefit Analysis sheet allows you to review the proposed project and potential alternatives and make a project selection based on a greater ROI (return on investment).
Risks | The Risk Management Matrix sheet allows you to identify, qualify, quantify, and prioritize risks (events that might happen; the uncertainty of a project), create mitigation and contingency plans, and assign risks owners.
Issues | The Issues Log sheet allows you to identify and monitor project issues (unplanned events that have happened).
Action | The Action Items sheet allows you to track and monitor action items assigned to team members. Action items are tasks that must be done but are too insignificant from a time perspective to track in your project schedule.
Miles | The Deliverable Milestones sheet allows you to identify major deliverable milestones and the due dates, objectives, assumptions, and constraints relevant to that deliverable milestone.
WBS | The Work Breakdown Structure sheet includes the activities that must be completed during a project, the effort required, all relevant dates, and the resources assigned to do the work.
Roster | The Roster sheet provides contact information for all those involved on the project.
R&R | The Roles and Responsibilities sheet shows the primary role of team members, any deliverables in which they are involved, and the percentage of time they are expected to work on the project.
RAM | The Resource Assignment Matrix sheet shows you what type of resource is responsible for, or somehow involved with, each deliverable. The tasks listed are samples; you should update the RAM with tasks appropriate for your project.
RCM | The Resource Commitment Matrix sheet shows how many effort hours each person on the project has been allocated by month.
A&C | The Assumptions and Constraints sheet allows you to track project assumptions and constraints.
Decision | The Decision Log sheet allows you to track all major decisions made during the course of the project.
Comm | The Communication Plan sheet allows you to detail your communication plan: how you are going to communicate, whom you will be communicating with, how often, in what format, etc.
Stake | The Stakeholder Analysis sheet allows you to identify stakeholders, their role, and their requirements.
Expectations | The Expectations sheet allows you to identify and track the expectations of various stakeholders.
Chg Log | The Change Control Log sheet allows you to track all change requests that are in process or finalized.
Deliver | The Deliverable Acceptance Log sheet allows you to track the status of deliverable acceptances.
PERT | The PERT Analysis sheet allows you to perform PERT analysis on WBS tasks.
Delphi | The Delphi Exercise sheet allows you to develop estimates for WBS tasks through the Delphi technique.
TimeSum | The Timesheet Totals sheet allows you to track effort hours of your entire team by individual and by month.
Timesheet | The Timesheet can be used by each team member to submit effort hours by activity, by month.
Size Est | The Initial Project Size Estimate sheet allows you to estimate, at high-levels (40,000 ft. view), the size of a project. This estimate should not be considered final as requirements and technical specifications typically have not been fully developed yet.
Res Load | The Resource Loading sheet allows you to identify the work effort required, the duration, and the allowed commitment level of each person assigned to the project.
Qual Metrics | The Project Quality Metrics sheet allows you to identify critical success criteria, related quality metrics, and their priority.
Project Register | The Project Register sheet allows you to identfy executive champions, goal/strategy alignment, and order of magnitude.
Portfolio Review | The Portfolio Review sheet identifies the CPI and SPI, status, and recommendations for each project in the portfolio.
© Global Knowledge Training LLC

## Data
Project | Personal Cybersecurity Risk Scanner
Project # | #12
Project manager | Mohammedreda El aroui
Sponsor | Mohamed AAZI
Project artifacts | https://github.com/project12/personal-cybersecurity-risk-scanner
Last updated | 2/4/2026
© Global Knowledge Training LLC

## Minicharter
Project Minicharter
Project |  | Project #
Project manager |  | Sponsor
Project artifacts |  | Updated
Background | Individuals and small organizations lack visibility into their cybersecurity posture. Many users unknowingly expose themselves through weak passwords, open ports, outdated software, or insecure configurations.
Business need and business benefits | Increase cybersecurity awareness for non-experts; Provide accessible and affordable risk assessment; Reduce exposure to common attacks; Enable proactive security practices; Potential SaaS tool for individuals or SMEs.
Objectives | 1. Develop a personal cybersecurity risk scanner tool. 2. Implement automated scanning of user environment. 3. Generate actionable risk scores and recommendations. 4. Deliver a simple dashboard/report for end-users.
Scope | In Scope | Out of Scope
Port scanning, password strength evaluation, vulnerability/config checking, risk scoring, dashboard
Enterprise security auditing, penetration testing, hardware security assessments, cloud deployment (v1)
Deliverables | Cybersecurity Risk Scanner (CLI/Desktop app) | Due Date
Risk Score Dashboard and Report Generator
User Documentation and Deployment Guide
Flexibility matrix | Scope
Schedule
Cost
Key considerations | Assumptions & Constraints | Risks
|  | Technical | Inaccurate vulnerability detection due to platform differences
|  | Scope | Scope creep from expanding feature requests
|  | Legal | Data privacy non-compliance (GDPR)
|  | Resource | Team member unavailability
|  | Financial | Budget overrun
Success criteria | Scanner accurately detects at least 90% of common vulnerabilities in test environment
Risk score is generated within 2 minutes of scan completion
Dashboard is rated as easy to use by at least 80% of beta testers
Zero data privacy breaches during testing and deployment phases
Project delivered on time and within the approved budget
Signatures
Sponsor
Signature
Printed name
Date
Project manager
Signature
Printed name
Date
© Global Knowledge Training LLC
Note on C16: Options are: Most flexible Moderately flexible Least flexible
Note on C17: Options are: Most flexible Moderately flexible Least flexible
Note on C18: Options are: Most flexible Moderately flexible Least flexible
Note on B19: Note A for assumptions, C for constraints
Note on C20: This is a field you can use to identify risks by categories such as technological, personnel, etc.

## Stoplight
Stoplight Report
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor
Project artifacts | [5 empty] | Updated
Deliverables
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Schedule
Scope
Cost
Risk
Issues
Planned completion
Est. completion
Management Alert
ID | Situation Requiring Management Attention |  |  |  | Action Plan |  |  |  | Owner
Accomplishments During Reporting Period
ID | Description of Accomplishment |  |  | Planned Completion | Date Completed | Owner |  | Comments
Deliverables | Title/Description |  |  |  |  | Title/Description
1 |  |  |  |  | 6
2 |  |  |  |  | 7
3 |  |  |  |  | 8
4 |  |  |  |  | 9
5 |  |  |  |  | 10
© Global Knowledge Training LLC
Note on B8: Options are: Green: On schedule/on budget Yellow: Somewhat behind schedule/somewhat over budget Red: Behind schedule/over budget
Note on A28: In Row 7 there are 10 deliverables listed. This section allows you to explain each deliverable.

## Budget
Budget
Project |  | Project #
Project manager |  | Sponsor
Project artifacts |  | Updated
Budget Status
Approved Budget | Planned Expenditures to Date | Actual Expenditures to Date | Variance
0 | 0 | 0
| Planned Remaining Budget | Actual Remaining Budget | Variance
Additional $ needed
Budget Details
Internal Expenses
Salaries | Hourly Rate | # Hours | Total Cost
Type of resource | 0 | 0
Type of resource | 0 | 0
Type of resource | 0 | 0
Type of resource | 0 | 0
Type of resource | 0 | 0
Type of resource | 0 | 0
Other Internal Expenses |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total Internal Expenses
External Expenses
Consulting Costs |  |  | Total Cost
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Capital Expenditures |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total External Expenses
Total Budget
© Global Knowledge Training LLC

## CBA
Cost/Benefit Analysis
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor
Project artifacts |  |  |  | Updated
Project Development and Maintenance Costs
Description | FY01 | FY02 | FY03 | FY04 | FY05 | Total
Cost of Project Development
Salaries
Other internal expenses
Consulting costs
Capital expenditures
Total project costs
Cost of Support
Operational costs
Nonrecurring costs
Recurring costs
Total ongoing support costs
Benefits/Savings
Current Process | FY01 | FY02 | FY03 | FY04 | FY05 | Total
Total annual price
New Process
Total annual price
Annual savings
Cumulative savings
Cumulative costs
Cumulative total net savings
Future Value
Present Value | Interest Rate |  | # Periods |  | Future Value
Present Value
Future Value | Interest Rate |  | # Periods |  | Present Value
Net Present Value
Period | Cash Flow |  |  |  | Present Value
1
2
3
4
5
Totals |  |  |  |  | 0
Project development cost |  |  |  |  | 0
Net present value
© Global Knowledge Training LLC
Note on A32: How much is the money worth today?
Note on D32: How many years will the project last?
Note on F32: This is how much money you expect the project to be worth.
Note on A36: This is how much money you expect the project to be worth.
Note on D36: How many years will it take until the company starts seeing this profit?
Note on F36: This is how much the money you project making would be worth in today's market.
Note on B40: FV for the period's return. Note: Change the PV # Periods to match the Period here.
Note on F40: This is how much the money you project making would be worth in today's market.

## Risks
Risk Management Matrix (Risk Register)
Project |  |  | Personal Cybersecurity Risk Scanner | [5 empty] | Project # | #12
Project manager |  |  | Mohammedreda El aroui | [5 empty] | Sponsor | Mohamed AAZI
Project artifacts | [8 empty] | Updated | 2/4/2026
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | Scope creep due to expanding feature requests | 3 | 4 | 2 | 12 | Scope | Stakeholder requests additional scan modules mid-project | Mitigate: Apply formal change control process; evaluate all new requests before approval | Freeze scope; defer new features to next release | Project Manager | Open | 2/4/2026 | 2026-05-01
2 | Data privacy breach during system scanning | 2 | 5 | 3 | 10 | Technical/Legal | Scanner accesses sensitive user data and logs are exposed | Mitigate: Encrypt all scan data; implement strict data handling policies | Halt scanning; notify affected users; apply data breach response plan | Security Lead | Open | 2/4/2026 | 2026-05-01
3 | Inaccurate vulnerability detection (false positives/negatives) | 3 | 4 | 3 | 12 | Technical/Quality | QA testing reveals scan results don't match real vulnerabilities | Mitigate: Extensive testing against known vulnerability datasets | Use third-party validation tools; recalibrate detection thresholds | Dev Lead | Open | 2/4/2026 | 2026-05-01
4 | Team member unavailability | 3 | 3 | 2 | 9 | Resource | Key developer leaves or is unavailable for an extended period | Mitigate: Cross-train team members; maintain up-to-date documentation | Redistribute tasks; bring in external consultant if needed | Project Manager | Open | 2/4/2026 | 2026-05-01
5 | Technology compatibility issues across OS platforms | 3 | 3 | 2 | 9 | Technical | Scanner fails on certain OS versions (Windows, Linux, macOS) | Mitigate: Early cross-platform testing in development phase | Limit scope to supported platforms; publish compatibility requirements | Dev Lead | Open | 2/4/2026 | 2026-05-01
6 | Budget overrun | 2 | 4 | 2 | 8 | Financial | Actual development costs exceed approved budget | Mitigate: Track expenditures weekly; use open-source tools | Request additional funding from sponsor; reduce non-critical features | Project Manager | Open | 2/4/2026 | 2026-05-01
7 | Schedule delay | 3 | 3 | 2 | 9 | Schedule | Sprint deliverables not completed on time due to technical complexity | Mitigate: Use Agile sprints with clear criteria; weekly status reviews | Re-baseline schedule; reallocate resources to critical path tasks | Project Manager | Open | 2/4/2026 | 2026-05-01
8 | Legal/Regulatory non-compliance | 2 | 5 | 3 | 10 | Legal/Compliance | Tool found to violate GDPR or local privacy laws during legal review | Mitigate: Conduct legal review early; consult data privacy expert | Suspend distribution; engage legal counsel; adjust data handling | Sponsor | Open | 2/4/2026 | 2026-05-01
9 | Low user adoption due to poor UX | 3 | 3 | 3 | 9 | Business | Beta testers find the dashboard confusing or not user-friendly | Mitigate: Conduct UX testing with non-technical users during development | Redesign UI based on feedback; provide user guides | Product Owner | Open | 2/4/2026 | 2026-05-01
10 | Third-party library vulnerabilities | 2 | 4 | 3 | 8 | Technical/Security | A dependency used in scanner has a known CVE | Mitigate: Use dependency scanning tools (e.g., Dependabot) in CI/CD | Patch or replace affected library immediately; re-test all modules | Dev Lead | Open | 2/4/2026 | 2026-05-01
11
12
13
14
15
© Global Knowledge Training LLC
Note on C6: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D6: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E6: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G6: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I6: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on L6: Options are: Open Closed

## Issues
Issues Log
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor
Project artifacts |  |  |  | Updated
ID | Issue Description | Project Impact | Action Plan/Resolution | Owner | Importance | Date Entered | Date to Review | Date Resolved
1 | What is the issue? | How will this impact scope, schedule & cost? | How do you intend to deal with this issue? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Training LLC
Note on F6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## Action
Action Items
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor
Project artifacts |  |  |  |  | Updated
ID | Action Item | Owner | Status | Date Entered | Planned Completion | Actual Completion | Comments
1 | Define project scope and deliverables | Mohammedreda El aroui | Completed | 2026-01-15 | 2026-01-20 | 2026-01-20 | Approved by sponsor
2 | Set up development environment | Dev Lead | Completed | 2026-01-20 | 2026-01-25 | 2026-01-24
3 | Research scanning libraries and tools | Dev Lead | Completed | 2026-01-25 | 2026-02-01 | 2026-02-01 | Selected nmap, bandit, zxcvbn
4 | Develop port scanning module | Dev Team | In Progress | 2026-02-01 | 2026-02-20
5 | Develop password strength evaluator | Dev Team | In Progress | 2026-02-01 | 2026-02-20
6 | Design risk scoring algorithm | Dev Lead | Not Started | 2026-02-10 | 2026-02-28
7 | Create dashboard/report UI | Dev Team | Not Started | 2026-02-15 | 2026-03-15
8 | Conduct internal QA testing | QA Team | Not Started | 2026-03-15 | 2026-03-30
9 | Conduct beta user testing | QA Team | Not Started | 2026-04-01 | 2026-04-15
10 | Legal/privacy compliance review | Data Privacy Officer | Not Started | 2026-03-01 | 2026-03-20
11
12
13
14
15
© Global Knowledge Training LLC
Note on D6: Options are: Open Closed

## Miles
Deliverable Milestones
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor
Project artifacts |  |  |  |  | Updated
ID | Milestone | Description | Planned Completion | Actual Completion | Objectives | Assumptions | Constraints
1 | Project Kickoff | Official start; team assembled and charter signed | 2026-01-10 | 2026-01-10 | Launch project with full team and sponsor approval | Funding approved before kickoff | Team must be available from day 1
2 | Requirements Finalized | All functional and technical requirements documented and approved | 2026-01-28 | 2026-01-28 | Clear scope baseline established | Stakeholders available for interviews | No scope changes after this milestone
3 | Architecture Design Complete | System design and tech stack approved | 2026-02-05 | 2026-02-05 | Technical blueprint ready for development | Dev tools and libraries selected | Must support Windows, Linux, macOS
4 | Core Scanning Modules Developed | Port scanner, password evaluator, config checker complete | 2026-03-10 |  | All primary scan features functional | Dev environment stable | Must pass internal unit tests
5 | Risk Scoring & Dashboard Complete | Risk algorithm and UI dashboard finalized | 2026-04-01 |  | Full product functionality achieved | Core modules tested and approved | UX review required
6 | QA Testing Complete | All internal and beta testing cycles finished | 2026-04-30 |  | Product meets quality standards | Beta users available for testing | All critical bugs resolved
7 | Project Closure | Final delivery, documentation, sponsor sign-off | 2026-05-07 |  | Successful handover to stakeholders | All deliverables accepted | Final report approved by sponsor
8
9
10
11
12
13
14
15
© Global Knowledge Training LLC

## WBS
Work Breakdown Structure
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor
Project artifacts | [5 empty] | Updated
ID | Task | Dependencies | Status | Effort Hours | Cost | Start Date | Planned Completion | Estimate to Completion | Actual Completion | Resource
1 | Project Initiation |  | Completed | 16 | 0 | 2026-01-10 | 2026-01-20 |  | 2026-01-20 | Mohammedreda El aroui
2 | Define scope and objectives | 1 | Completed | 8 | 0 | 2026-01-10 | 2026-01-15 |  | 2026-01-15 | Mohammedreda El aroui
3 | Stakeholder identification | 1 | Completed | 4 | 0 | 2026-01-12 | 2026-01-16 |  | 2026-01-16 | Mohammedreda El aroui
4 | Project planning and scheduling | 2,3 | Completed | 12 | 0 | 2026-01-15 | 2026-01-22 |  | 2026-01-22 | Mohammedreda El aroui
5 | Requirements gathering | 4 | Completed | 20 | 0 | 2026-01-18 | 2026-01-28 |  | 2026-01-28 | Dev Lead
6 | System architecture design | 5 | Completed | 16 | 0 | 2026-01-25 | 2026-02-05 |  | 2026-02-05 | Dev Lead
7 | Set up development environment | 6 | Completed | 8 | 0 | 2026-02-01 | 2026-02-07 |  | 2026-02-07 | Dev Team
8 | Develop port scanning module | 7 | In Progress | 30 | 0 | 2026-02-08 | 2026-02-20 | 2026-02-20 |  | Dev Team
9 | Develop password strength evaluator | 7 | In Progress | 20 | 0 | 2026-02-08 | 2026-02-20 | 2026-02-20 |  | Dev Team
10 | Develop vulnerability/config checker | 8,9 | Not Started | 40 | 0 | 2026-02-20 | 2026-03-10 | 2026-03-10 |  | Dev Team
11 | Develop risk scoring algorithm | 10 | Not Started | 24 | 0 | 2026-03-01 | 2026-03-15 | 2026-03-15 |  | Dev Lead
12 | Build dashboard/report UI | 11 | Not Started | 40 | 0 | 2026-03-10 | 2026-04-01 | 2026-04-01 |  | Dev Team
13 | Internal QA testing | 12 | Not Started | 20 | 0 | 2026-04-01 | 2026-04-15 | 2026-04-15 |  | QA Team
14 | Beta user testing | 13 | Not Started | 16 | 0 | 2026-04-15 | 2026-04-30 | 2026-04-30 |  | QA Team
15 | Project closure and documentation | 14 | Not Started | 12 | 0 | 2026-04-30 | 2026-05-07 | 2026-05-07 |  | Mohammedreda El aroui
© Global Knowledge Training LLC
Note on D6: Options are: Open Closed

## Roster
Roster
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor
Project artifacts |  |  |  |  | Updated
Name | Core/ Extended Team | Title | Dept. | Phone | Cell Phone | E-Mail | Project Role
|  |  |  | 000.000.0000 | 000.000.0000
© Global Knowledge Training LLC

## R&R
Roles and Responsibilities
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor
Project artifacts |  |  |  |  | Updated
Name | Core/ Extended Team | % Assigned | Deliverables Leading | Deliverables Participating On | Project Role | Responsibility | Other Project Assignments
© Global Knowledge Training LLC

## RAM
Resource Assignment Matrix
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor
Project artifacts |  |  |  | Updated
Project Task
Project Management and Requirements
Initiation
1
2
3
4
5
Planning
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
Execution
1
2
3
4
5
6
Closing
1
2
3
4
5
6
7
Legend
| Creates the deliverable |  | C1: primary creator; C2: contributor
| Input required |  | I
| Reviews the deliverable |  | R
| Approves the deliverable |  | A
| Notified when the deliverable is complete |  | N
| Owns the deliverable upon completion |  | O
© Global Knowledge Training LLC
Note on E6: Insert team member roles in this row.
Note on D10: Insert project tasks for this phase in this column.
Note on D17: Insert project tasks for this phase in this column.
Note on D42: Insert project tasks for this phase in this column.
Note on D50: Insert project tasks for this phase in this column.

## RCM
Resource Commitment Matrix
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor
Project artifacts | [5 empty] | Updated
Effort Hours Committed
Names | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
Total
© Global Knowledge Training LLC

## A&C
Assumptions and Constraints
Project |  |  | Project #
Project manager |  |  | Sponsor
Project artifacts |  |  | Updated
ID | Description | Comments | Type | Status | Date Entered
1 | The scanner will run on Windows, Linux, and macOS systems |  | Assumption | Active | 2/4/2026
2 | Users will have basic internet access to receive updates |  | Assumption | Active | 2/4/2026
3 | Open-source libraries (nmap, bandit, zxcvbn) will be used to reduce costs |  | Assumption | Active | 2/4/2026
4 | The project budget is fixed and approved by the sponsor |  | Constraint | Active | 2/4/2026
5 | Project must be completed by May 7, 2026 |  | Constraint | Active | 2/4/2026
6 | All user data collected must comply with GDPR |  | Constraint | Active | 2/4/2026
7 | Scanner must be able to run offline (no internet required during scan) |  | Assumption | Active | 2/4/2026
8 | Team has necessary technical skills in Python and network security |  | Assumption | Active | 2/4/2026
9 | Third-party threat intelligence APIs will remain available throughout |  | Assumption | Active | 2/4/2026
10 | v1 will be a desktop/CLI tool, not a cloud service |  | Constraint | Active | 2/4/2026
11
12
13
14
15
© Global Knowledge Training LLC
Note on D6: Options are: A: assumption C: constraint
Note on E6: Options are: Open Closed

## Decision
Decision Log
Project |  |  | Project #
Project manager |  |  | Sponsor
Project artifacts |  |  | Updated
ID | Decision Description | Comments | Owner | Status | Date Entered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Training LLC
Note on D6: Who made the decision?
Note on E6: Options are: Open Closed

## Comm
Communication Plan
Project |  |  | Project #
Project manager |  |  | Sponsor
Project artifacts |  |  | Updated
ID | Communication | Description | Frequency | Format | Owner | Recipient/ Attendees
1 | Weekly Status Meeting | Review sprint progress, blockers, and action items | Weekly | Video call / Meeting notes | Mohammedreda El aroui | All team members
2 | Sponsor Update Report | High-level project status, budget, risks for sponsor | Bi-weekly | Email report | Mohammedreda El aroui | Mohamed AAZI
3 | Sprint Review | Demo of completed features to stakeholders | End of each sprint | Live demo / Presentation | Dev Lead | Sponsor, PM, QA
4 | Risk Review | Review and update risk register | Monthly | Risk register document | Mohammedreda El aroui | All team members
5 | Change Request Notification | Notify stakeholders of scope/schedule change requests | As needed | Email + Change log | Mohammedreda El aroui | Sponsor, Dev Lead
6 | Project Kickoff Meeting | Introduce project goals, team, plan, and timeline | Once (project start) | In-person / Video call | Mohammedreda El aroui | All stakeholders
7 | User Testing Report | Share findings from beta user testing sessions | End of testing phase | Written report + Dashboard | QA Lead | PM, Sponsor
8 | Project Closure Report | Document final deliverables, lessons learned, sign-off | Project end | Final report document | Mohammedreda El aroui | Mohamed AAZI, All team
9
10
11
12
13
14
15
16
17
© Global Knowledge Training LLC
Note on E6: Examples: E-mail Meeting
Note on B7: Examples: Executive status report Team status report

## Stake
Stakeholder Analysis
Project |  |  | Project #
Project Manager |  |  | Sponsor
Project Artifacts |  |  | Updated
ID | Stakeholder | Role | Impact | Influence | Risk Tolerance | Needs | Responsibility
1 | Mohamed AAZI | Project Sponsor | High | High | Low | On-time delivery, budget compliance | Approve budget and scope changes
2 | Mohammedreda El aroui | Project Manager | High | High | Medium | Clear requirements and team support | Plan, execute, monitor project
3 | Development Team | Technical Developers | High | Medium | Medium | Clear specs, tools, and environment | Build and test the scanner
4 | End Users (Individuals/SMEs) | Primary Users | High | Low | Medium | Simple, accurate, actionable tool | Use tool and provide feedback
5 | Data Privacy Officer | Compliance Advisor | Medium | High | Low | GDPR compliance, data minimization | Review data handling procedures
6 | QA/Testing Team | Quality Assurance | Medium | Medium | Medium | Test cases and requirements docs | Test and validate scanner output
7
8
9
10
11
12
13
14
15
© Global Knowledge Training LLC
Note on D6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on E6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## Expectations
Expectations
Project |  | Project #
Project manager |  | Sponsor
Project artifacts |  | Updated
ID | Expectation Description | Source | Must Have | Want to Have | Nice to Have | Date Identified
© Global Knowledge Training LLC

## Chg Log
Change Control Log
Project | [5 empty] | Project #
Project Manager | [5 empty] | Sponsor
Project Artifacts | [5 empty] | Updated
ID | Change Description | Priority | Originator | Date Entered | Date Assigned | Evaluator | Status | Date of Decision | Included in Rev. #
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Training LLC
Note on C6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on D6: Who identified the change needed?
Note on G6: Who will decide what action is taken on the change?
Note on H6: Options are: In review Rejected Deferred Approved
Note on J6: Options are: No Rev. #

## Deliver
Deliverable Acceptance Log
Project |  |  | Project #
Project manager |  |  | Sponsor
Project artifacts |  |  | Updated
ID | Deliverable Description | Comments | Evaluator | Status | Date of Decision
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
© Global Knowledge Training LLC
Note on E6: Options are: In review Rejected Accepted

## PERT
PERT Analysis
Project | [7 empty] | Project #
Project Manager | [7 empty] | Sponsor
Project Artifacts | [7 empty] | Updated
ID | Task | Most Likely | Min | Max | PERT Est | 15/15 Comp'ed Est | Std Dev | +1 Std Dev | -1 Std Dev | +2 Std Dev | -2 Std Dev | +3 Std Dev | -3 Std Dev
© Global Knowledge Training LLC

## Delphi
Delphi Exercise
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor
Project artifacts | [5 empty] | Updated
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely
Minimum
Maximum
© Global Knowledge Training LLC

## TimeSum
Timesheet Totals
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor
Project artifacts | [5 empty] | Updated
Effort Hours Spent
Name | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
Total
© Global Knowledge Training LLC

## Timesheet
Timesheet
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor
Project artifacts | [5 empty] | Updated
Name | Insert name here
Effort Hours Spent
Task | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
Total
© Global Knowledge Training LLC

## Size Est
Initial Project Size Estimate
Project |  |  | Project #
Project manager |  |  | Sponsor
Project artifacts |  |  | Updated
Scope Estimate
Technology Systems Impacted
|  | 1 to 2 | 3 to 5 | 6 or more
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
Benefit | Low |  |  | Avoid
Medium
| High | Automatically do; no approval needed
© Global Knowledge Training LLC

## Res Load
Resource Loading
Project | Project title here |  | Project # | Project # here
Project manager | Project manager name here |  | Sponsor | Sponsor name here
Project artifacts | Location of project documents here |  | Updated | Date of update here
Team Member:
Effort Hours Committed
ID | Task | Effort Hours | Duration (Weeks) | Available Hours | Commitment Level
Total
© Global Knowledge Training LLC
Note on C7: Estimate of total hours needed for this task
Note on E7: Number of hours that member has available
Note on F7: Available Hours divided by Duration (Weeks). However, if Effort Hours is less than Available Hours, then Effort Hours divided by Duration (Weeks).

## Qual Metrics
Project Quality Metrics
Project |  |  | Project #
Project Manager |  |  | Sponsor
Project Artifacts |  |  | Updated
ID | Critical Success Criteria | Potential Quality Metric |  | Priority | Metric Target | Action Plan
© Global Knowledge Training LLC

## Project Register
Project Register
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor
Project artifacts |  |  |  | Updated
Order of Magnitude
ID | Project Name | Description | Category | Executive Champion | Goal/Strategy Alignment | Time | Costs | Return | Status | Rank
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on C7: Brief description of proposed project
Note on D7: Type of project (e.g., product development, market expansion, legal requirement, regulatory mandate, strategic)
Note on E7: Executive team member serving as primary champion or "cheerleader" for the project
Note on F7: Organizational goals and/or strategic objectives that align with project
Note on G7: Options are: 4: > 2 years 3: > 1 year 2: 6 - 12 months 1: 0 - 6 months
Note on H7: Options are: 4: > $1 million 3: > $500,000 2: $100,000 - $500,000 1: Up to $100,000
Note on I7: Options are: 4: 1 - 6 months 3: 6 - 24 months 2: 2 years+ 1: never
Note on J7: Options are: Active Approved Rejected Under review Postponed
Note on K7: Priority of this project compared to the other projects in the portfolio

## Portfolio Review
Periodic Portfolio Review Report
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor
Project artifacts |  |  |  | Updated
|  |  |  | Analysis |  | Status
ID | Project Name | Description | Rank | Costs (CPI) | Schedule (SPI) | Time | Costs | Scope | Return | Recommendation
1
2
3
4
5
6
7
8
Periodic Portfolio Review Report
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor
Project artifacts |  |  |  | Updated
|  |  |  | Analysis |  | Status
ID | Project Name | Description | Rank | Costs (CPI) | Schedule (SPI) | Time | Costs | Scope | Return | Recommendation
9
10
11
12
13
14
15
Note on G6: Options: Red: Significantly off target Yellow: Off target or trending outside of acceptable limits Green: On target Blue: Requires executive attention or awaiting critical decision(s)
Note on K7: Options: Proceed Cancel Suspend Re-Prioritize
Note on G21: Options: Red: Significantly off target Yellow: Off target or trending outside of acceptable limits Green: On target Blue: Requires executive attention or awaiting critical decision(s)
Note on K22: Options: Proceed Cancel Suspend Re-Prioritize